## Build Plan v4
ommphone · Build Plan v4 · iPhone 13 mini · pickup-to-pulse
Hold device → beat + warmth auto-start · Put down → fade + cool · v4 firmware
Step | Phase | Action | Files / Parts | Vendor | Est. Time | Cost | Status
1 | Review | Send everything to embedded engineer | omphone_manufacturing_files_v3.zip omphone_BOM_v3.csv · omphone_CPL_v3.csv omphone_firmware_v4.zip omphone_front_2buttons.stl omphone_back_2buttons.stl | ITviec/TopDev | 1–2 days | $200–300 | Pending
2 | Review | Engineer checks Gerbers in EasyEDA/KiCad | Trace widths · clearances · CPL rotations nRF52832 antenna keepout SW1/SW2 at board edges (X=4 & X=54, Y=39) | Engineer | 1 day | — | Pending
3 | Review | Engineer checks TTP223 pad size | Current pad: 25mm diameter Recommend: enlarge to 25mm OR add 2nd pad on back face for reliable palm-grip detection Firmware polls P0.05 every 50ms | Engineer | 1 hr | — | Pending
4 | Review | Engineer confirms button alignment with STL | SW1 X=4mm Y=39mm → left edge hole SW2 X=54mm Y=39mm → right edge hole 6×6mm PTS525 must fit within 1.6mm wall | Engineer | 1 hr | — | Pending
5 | Review | Engineer compiles firmware v4 | omphone_firmware_v4.zip Verify touch poll 50ms · pickup debounce 200ms Putdown debounce 1500ms · heat ramp 0/5/15s | Engineer | 2 hrs | — | Pending
6 | Order PCB | Upload Gerbers to JLCPCB | omphone_manufacturing_files_v3.zip jlcpcb.com → Order Now → Upload | JLCPCB | 15 min | — | Pending
7 | Order PCB | Configure board settings | Layers: 2 · Size: 58×118mm · FR4 1.6mm HASL lead-free · Black solder mask | JLCPCB | 5 min | — | Pending
8 | Order PCB | Enable SMT Assembly → upload BOM + CPL | omphone_BOM_v3.csv (23 components) omphone_CPL_v3.csv SW1+SW2 PTS525 included | JLCPCB | 15 min | $75–95 | Pending
9 | Enclosure | Upload STLs to JLC3DP | omphone_front_2buttons.stl omphone_back_2buttons.stl jlc3dp.com → Upload both | JLC3DP | 10 min | — | Pending
10 | Enclosure | Configure print settings | Material: SLA resin · Color: Black Finish: Matte · Qty: 2 of each shell | JLC3DP | 5 min | $25–40 | Pending
11 | Parts | Order LiPo battery | LiPo 100mAh 3.7V JST-PH · Adafruit #1570 Red wire = positive · connect to J4 | Adafruit | online | $5–8 | Pending
12 | Parts | Order motor + NTC + heater pad | 12mm coin motor 3V → J2 NTC 10k JST-PH leads 80mm → J3 Flexible 5V 15×25mm pad → J1 | Amazon | online | $18–25 | Pending
13 | Parts | Order cables + programmer | JST-PH 100mm cables pack J-Link EDU Mini (one-time) | Amazon | online | $25–32 | Pending
14 | Flash | PCBs arrive — inspect all 23 components | Check SW1 left edge · SW2 right edge protrude Verify TTP223 pad visible on PCB surface No cold solder joints on QFN48 nRF52832 | — | 30 min | — | Pending
15 | Flash | Flash firmware v4 | make flash_softdevice ← once only make flash SWD: VCC · GND · SWDIO · SWDCLK → J-Link | J-Link EDU Mini | 20 min | — | Pending
16 | Test | Verify pickup-to-pulse behaviour | ★ KEY TEST — no buttons needed: 1. Hold device in palm 2. Within 200ms → feel 1 gentle throb 3. Warmth starts at LOW 4. After 5s → warmth increases to MED 5. After 15s → full warmth + strong beat 6. Put down → beat fades over 5 pulses 7. Heat stops immediately on putdown | — | 15 min | — | Pending
17 | Test | Verify button overrides | Tap LEFT → beat stops (2 blinks) Tap LEFT again → beat resumes (1 blink) Tap RIGHT → heat stops (4 blinks) Tap RIGHT again → heat resumes (3 blinks) Hold LEFT 1.5s → airplane (5 rapid blinks) Hold RIGHT 3s → power off (1 long pulse) | — | 10 min | — | Pending
18 | Test | Verify BLE proximity | Hold 2× ommphones near each other Beat should quicken as they approach Heat should increase with proximity Within 3m: beats phase-lock simultaneously | — | 10 min | — | Pending
19 | Assemble | Final assembly | 1. LiPo into battery pocket (top zone back tray) 2. PCB into pocket — buttons align with holes 3. Connect J1 heat · J2 motor · J3 NTC · J4 LiPo 4. Snap front onto back (×4 corner tabs) 5. USB-C slot aligns at bottom edge | — | 45 min | — | Pending
COST SUMMARY — v4
JLCPCB PCB + Assembly (5 units) |  |  |  |  | $75–95 |  | 23 components incl. SW1+SW2
JLC3DP SLA enclosure (×2 front + back) |  |  |  |  | $25–40 |  | Black matte resin
Off-board parts (LiPo/motor/NTC/heater/cables) |  |  |  |  | $53–85 |  | See parts list
J-Link EDU Mini |  |  |  |  | $18–25 |  | One-time reusable
TOTAL (5 prototypes) |  |  |  |  | $171–245 |  | ~$40–49 per unit
PRODUCTION 500 units Vietnam |  |  |  |  | ~$10.16/unit |  | Pickup-to-pulse · no extra cost vs v3